Datalab V

Quincy Soerohardjo

Jassar Hasiba

Jesse Coenraad

Lars Timmer

Developing an AI-based predictive model for drought and flood early warning systems in African agriculture for Lidi Smart Solutions

2026

1. Business and problem context	3

2. Background and problem definition	4

3. Goals	5

4. Provisional research question and sub-questions	6

5. Planning	9

6. Risk Analysis	10

6.1 Analysis of critical risks	11

6.2 Conclusion	12

7. Final qualifications	13

Reference list	14

# 1. Business and problem context

Lidi Smart Solutions is an organization, based in The Hague, the Netherlands, involved in several projects funded by the European Union. The company's core activities focus on digital innovation, artificial intelligence (AI), and sustainability.

This specific assignment is being carried out for the AI4AgriBizAfrica concept, which is currently under development within the Horizon Europe framework. The objective of this concept is to improve climate and weather models in Africa by leveraging AI and open data technologies (Horizon Europe, 2026). Within this domain, the focus is on the vulnerability of African agriculture to climate variability. Approximately 95% of African farmers depend entirely on rain-fed systems, meaning that shifting weather patterns directly threaten national food security and rural livelihoods (Gashure, 2024; Muzata, n.d.). Consequently, extreme weather conditions such as droughts and floods can lead to total crop failure, mass livestock mortality, and long-term economic instability for smallholder farming communities (Balgah et al., 2023). The timing of this project is directly tied to the active development of the AI4AgriBizAfrica initiative within Horizon Europe and the growing availability of open climate datasets such as ERA5, which together create a concrete opportunity to address this gap now.

This project utilizes open climate reanalysis data from the Copernicus Climate Data Store (ERA5). This dataset consists of six atmospheric parameters measured on an hourly basis across the African continent (ERA5: Data Documentation - Copernicus Knowledge Base - ECMWF Confluence Wiki, 2026). This data will be made available via a Microsoft Azure cloud storage environment.

# 2. Background and problem definition

The motivation for this assignment is the urgent need to strengthen agricultural resilience in Africa and support farmers' decision-making. Climate disasters such as droughts and floods cause significant economic damage and threaten livelihoods across the continent (Reed et al., 2022; Balgah et al., 2023). Floods damage crops and infrastructure, directly threatening food security across African regions, while droughts lead to livestock deaths, force farmers to abandon their land and cause lasting economic damage to rural communities (Balgah et al., 2023; Monnik, 2000). As climate change progresses, these extreme events are becoming more frequent, making timely intervention increasingly urgent (Motha, 2000). Timely and reliable information provided through Early Warning Systems (EWS) can help farmers make better decisions regarding planting, irrigation, and risk mitigation (CWP, 2025). However, existing systems fall short in three concrete ways.

First, drought develops as a creeping phenomenon without a clearly identifiable onset point, making it inherently difficult to detect before damage has already occurred (Wilhite & Svoboda, 2000). Unlike a flood, which produces a discrete observable event, drought onset must be inferred from multi-week or multi-month accumulations of precipitation deficits, temperature anomalies, and soil moisture trends. None of which cross a universally agreed threshold (Wilhite & Svoboda, 2000). For example, the Standardized Precipitation Index (SPI) is commonly used to flag drought when cumulative rainfall falls more than one standard deviation below the 30-year climatological mean for a given region and season, yet the appropriate time window (1, 3, 6, or 12 months) varies by agricultural system and region (Nandgude et al., 2023). Defining a consistent, reproducible target variable for the machine learning model is therefore a non-trivial methodological challenge. Second, although large volumes of open climate data such as ERA5 are freely available, they rarely reach the farmers who need them the most, due to poor infrastructure, low digital literacy and a persistent gap between receiving a warning and knowing what to do with it (Hansen et al., 2019; Choruma et al., 2024). Third, local institutions across Africa generally lack access to AI-driven tools capable of translating raw meteorological parameters into clear, actionable risk signals (Nandgude et al., 2023; Ferchichi et al., 2023).

The core problem is therefore specific and threefold: early signals of drought and flooding are hidden within complex atmospheric patterns, available climate data remains untapped at the local level, and no accessible tool currently exists that can translate these meteorological parameters into practical early warnings for non-technical users.

The scale and structure of the data add a further layer of technical complexity. ERA5 provides hourly estimates of atmospheric variables at a spatial resolution of approximately 31 km across the entire African continent, extending from 1940 to the present (ERA5: Data Documentation - Copernicus Knowledge Base - ECMWF Confluence Wiki, 2026). For a single grid cell, this amounts to roughly 745,000 hourly observations per variable over 85 years. With six atmospheric variables, including temperature, precipitation, wind speed, and humidity, each grid cell yields approximately 4.5 million data points before any feature engineering is applied. Across a study region of even modest size (e.g., 100 × 100 grid cells), the dataset rapidly grows into the billions of records, requiring careful selection of temporal scope and spatial extent to remain computationally tractable. Beyond data volume, the modelling task itself is inherently complex. Drought and flood events are by nature rare creating a severe class imbalance that standard machine learning algorithms are not designed to handle without adjustment (Nandi, 2025). Moreover, climate data is temporally ordered: each observation depends on those that preceded it, violating the assumption of independence that underpins conventional train-test splitting. Failure to account for this temporal structure leads to data leakage, where future information leaks into model training and inflates apparent performance (Chalokia, 2021). Finally, the relationships between raw atmospheric variables and the onset of a drought or flood are inherently non-linear: drought severity depends not only on current precipitation but on accumulated deficits over weeks or months interacting with temperature and evaporation rates, while floods can be triggered by short, intense precipitation events in combination with soil saturation conditions (Nandgude et al., 2023; Ferchichi et al., 2023). These non-linear, multi-variable dependencies make the problem substantially harder than standard tabular classification tasks and require domain-informed feature engineering as a prerequisite to effective modelling.

# 3. Goals

The primary deliverable of this project is a technically robust proof-of-concept machine learning model that predicts the probability of onset drought and floods based on ERA5 climate parameters. However, the value of this project extends beyond the model itself.

For Lidi Smart Solutions, this proof-of-concept directly enables the organization to give concrete shape to the AI4AgriBizAfrica initiative within the Horizon Europe framework. Currently, local institutions across Africa lack access to AI-driven tools capable of translating raw meteorological data into clear, actionable risk signals (Nandgude et al., 2023; Ferchichi et al., 2023).

For the end users, agricultural advisors and policymakers, the working prototype will present drought and flood risk through easy-to-understand visualizations and risk scores. This is a critical distinction from existing Early Warning Systems, which often rely on technical probabilistic forecasts that non-technical users struggle to translate into practical decisions as when to plan, irrigate or prepare for crop stress (Hansen et al., 2019).

Beyond the deliverable itself, the organizational impact consists of three distinct elements. First, it demonstrates to stakeholders and EU Funders that an AI-driven early warning system is technically feasible using open ERA5 data. Second, it provides a foundation that can be extended toward operational deployment in specific African Regions, contributing to reduced agricultural losses and improved household resilience among smallholder farmers (Teku & Tariku, 2025). Third, it equips Lidi Smart Solutions with a validated methodology and codebase that can be built upon in follow-up projects within the AI4AgriBizAfrica initiative.

Success is therefore explicitly defined not by model performance metrics alone, but by whether the output is understandable, applicable, and valuable to the non-technical stakeholders it is designed to serve. To make this measurable, the prototype will be validated with at least one non-technical stakeholder to assess whether the risk outputs are interpretable and actionable in practice.

# 4. Provisional research question and sub-questions

Based on the needs of the primary stakeholders, the chosen research question is: How can a machine learning model, trained on daily ERA5 atmospheric data, predict the onset of agricultural drought (operationalised through a combination of the Standardized Precipitation Evapotranspiration Index (SPEI) and the Soil Moisture Index (SMI)) and flood risk (operationalised through a combination of total runoff and the Antecedent Precipitation Index (API)) in sub-Saharan African agricultural regions, with sufficient lead time to support early warning decisions? (Vicente-Serrano et al., 2010; Fedora & Beschta, 1989).

This leads to the following sub-questions:

| Phase (Crisp-DM) | Sub question | Methods |
| --- | --- | --- |
| Business understanding | How can predictive machine learning model contribute to a reliable and practical warning system for droughts and floods in African agricultural regions? | Literary research (Baarda & Van Vianen, 2021, pp. 64–78) – Used to establish a theoretical foundation for the context of the problem and justify the relevance of the project. Stakeholder analysis – Conducted to identify the needs and constraints of end users. Problem definition and desk research – applied to systematically map existing solutions and their limitations. Definition of success criteria – established to ensure the project is evaluable. |
| Data understanding | What are the characteristics, quality and limitations of ERA5 climate dataset? To what extend is the dataset suitable for predicting drought and flood risk? | Exploratory Data Analysis (Jha, 2025) – applied to gain insights into the distribution, range and patterns of the ERA5 atmospheric variables before any modelling takes place. Data validation (Prometeia, 2025) – used to detect missing values, inconsistencies and noise that could have a negative impact on the model’s reliability. |
| Data preparation | How can the raw ERA5 climate variables be transformed into meaningful, model-ready features that operationalise drought risk through SPEI and SMI, and flood risk through total runoff and API? | Feature engineering (Francis, 2024) – applied because raw ERA5 variables such as temperature and precipitation do not directly represent drought or flood risk and must be transformed into meaningful indicators. For drought, SPEI is derived from precipitation and potential evapotranspiration to capture multi-scalar moisture deficits, while SMI normalises modelled soil water content between wilting point and field capacity (Vicente-Serrano et al., 2010; Copernicus European Drought Observatory, 2019). For flood risk, total runoff from ERA5 captures both surface and sub-surface water flux, while the Antecedent Precipitation Index (API) provides a decaying-weighted accumulation of preceding rainfall to represent catchment wetness prior to a flood event (Fedora & Beschta, 1989). Feature selection (Belcic & Stryker, n.d.) – used to reduce dimensionality and retain only those variables that contribute meaningfully to prediction. Normalization / standardization (AbhijeetDataVision, 2025) – applied to ensure that variables measured on different scaled do not disproportionately influence model outcomes. Handling class imbalance (Nandi, 2025) – likely necessary because droughts and flood events are by nature rare occurrences. Whether this applies will be confirmed after target variable definition. Time-based train/test split (Chalokia, 2021) – chosen specifically over random splitting to prevent data leakage, as climate data is temporally ordered and future values must not influence the model training process. |
| Modelling | Which machine learning models provide the best balance between reliable and interpretable predictions of drought and flood risk? | Model comparison (Devansh, 2023) – applied to identify which model best captures the non-linear relationships between atmospheric variables and climate risk. Hyperparameter tuning (Singh, 2024) – used to optimize model configuration and improve predictive performance beyond the default settings. Performance evaluation (Caballar & Stryker, n.d.) – applied to use metrics that are appropriate the final model task. Overfitting / underfitting analysis (Stuart, 2025) – conducted to ensure the model generalizes to unseen data rather than memorizing patterns. Feature importance analysis (Bhuva, 2025) – used to make the model more interpretable and to validate that the most influential variables align with the domain knowledge. |
| Evaluation | To what extend does the developed model meet the technical, societal and practical objectives of the project? | Assessment of model performance against predefined project goals and success criteria – to determine whether the model meets the success criteria that were predefined. Analysis of generalizability by comparing performance across different time periods – to test whether the model performs consistently outside its training window. Analysis of error types (Relangi, 2024) – applied to distinguish between false positives and false negatives, as missing a drought or flood event brings greater real-world consequences than a false alarm. Scenario analysis and Ethical evaluation – conducted to reflect on potential bias, regional limitations and responsible use of the model as a decision-support tool. Writing a final report (Baarda & Van Vianen, 2021, pp. 279–302) – structured according to academic reporting guidelines to ensure findings are communicated clearly, reproducibly and in a format accessible to both technical and non-technical stakeholders. |

# 5. Planning

This project is structured according to the CRISP-DM (CRoss Industry Standard Process for Data Mining) methodology, which provides an iterative, industry-independent process model for executing data-driven and machine learning projects (Wirth & Hipp, 2000; Chapman et al., 2000). CRISP-DM comprises six phases: Business Understanding, Data Understanding, Data Preparation, Modelling, Evaluation, and Deployment. These phases are not strictly sequential; they allow for back-and-forth iteration as insights from later phases may require revisiting earlier ones. In this project, the Deployment phase is replaced by the creation of a proof-of-concept and a final report, as full operational deployment falls outside the scope of this graduation project. The table below presents the planning of this project, with each row corresponding to a CRISP-DM phase, the methods applied, the intermediate product delivered, and the estimated timeframe.

| Phase | Method | Intermediate product | Time |
| --- | --- | --- | --- |
| Analysing the climate variables related to onset drought and floods. | Literary analysis | Literary report and justify feature selection. | Week 1-7 |
| Obtain and prepare ERA5 climate data. | Configuring azure environment, setup api links for era5 extraction, data cleaning in Python. | Clean dataset. | Week 5-9 |
| Transforming meteorological parameters to significant features. | Feature engineering through techniques such as imputation, encoding, scaling and creating new variables such as SPEI and SMI. | Dataset including derived and defined target variables. | Week 8-12 |
| Model creation and testing | Testing different models (Xgboost and LSTM) for later comparison and proper baselines. Models will be chosen based on earlier research. | Trained ML-models | Week 10-14 |
| Evaluate model results, robustness, and reliability. | Validation techniques such as K-Fold Cross validation and evaluation metrics such as F1-score. | Evaluation report with model comparison and feature importance. | Week 13-17 |
| Create visualisation and ethical reflection and final report. | Data visualization and structured report. | Final report with proof-of-concept and presentation. | Week 14-18 |

The following section elaborates on the methods applied within each CRISP-DM phase and explains how these methods connect to the project's research questions and objectives.

## 5.1 Business Understanding

The Business Understanding phase focuses on translating the organizational problem into a data science objective. In this project, this phase involves establishing the theoretical and contextual foundation of the problem through literary research (Baarda & Van Vianen, 2021). A structured literature review is conducted to identify existing knowledge on drought and flood dynamics in sub-Saharan Africa, the limitations of current early warning systems, and the applicability of machine learning in this domain. In addition, a stakeholder analysis is performed to map the needs and constraints of end users, including agricultural advisors and policymakers at Lidi Smart Solutions. Finally, success criteria are defined to ensure the project remains evaluable and practically relevant throughout its execution.

## 5.2 Data Understanding

The Data Understanding phase involves exploring and assessing the quality of the ERA5 climate dataset before any modelling takes place. Exploratory Data Analysis (EDA) is applied to gain insight into the distribution, range, and temporal patterns of the atmospheric variables (Jha, 2025). This is complemented by data validation techniques to detect missing values, outliers, and inconsistencies that could negatively affect model reliability (Prometeia, 2025). The outcome of this phase is a clean, well-understood dataset that serves as the foundation for subsequent data preparation.

## 5.3 Data Preparation

The Data Preparation phase transforms raw ERA5 variables into model-ready features. Feature engineering is the central method in this phase: raw atmospheric variables such as temperature and precipitation do not directly represent drought or flood risk and must be converted into meaningful indicators (Francis, 2024). For drought, the Standardized Precipitation Evapotranspiration Index (SPEI) is derived to capture multi-scalar moisture deficits, and the Soil Moisture Index (SMI) normalizes modelled soil water content between wilting point and field capacity (Vicente-Serrano et al., 2010; Copernicus European Drought Observatory, 2019). For flood risk, total runoff from ERA5 is combined with the Antecedent Precipitation Index (API), which provides a decaying-weighted accumulation of preceding rainfall to represent catchment wetness (Fedora & Beschta, 1989). Feature selection is then applied to reduce dimensionality and retain only variables that contribute meaningfully to prediction (Belcic & Stryker, n.d.). Normalization and standardization ensure that variables measured on different scales do not disproportionately influence model outcomes (AbhijeetDataVision, 2025). Because droughts and floods are rare events, class imbalance handling may be required (Nandi, 2025). Finally, a time-based train/test split is applied specifically to prevent data leakage, since climate data is temporally ordered and future values must not influence the training process (Chalokia, 2021).

## 5.4 Modelling

The Modelling phase focuses on selecting, training, and optimizing machine learning models. Model comparison is applied to identify which algorithm best captures the non-linear relationships between atmospheric variables and climate risk (Devansh, 2023). Subsequently, hyperparameter tuning is conducted to optimize the model's configuration beyond default settings (Singh, 2024). Model performance is evaluated using metrics appropriate to the classification task, such as precision, recall, and the F1-score (Caballar & Stryker, n.d.). Overfitting and underfitting analysis is performed to ensure the model generalizes to unseen data rather than memorizing training patterns (Stuart, 2025). Finally, feature importance analysis is used to make the model interpretable and to validate that the most influential variables align with domain knowledge about drought and flood dynamics (Bhuva, 2025).

## 5.5 Evaluation

The Evaluation phase assesses whether the developed model meets the technical, societal, and practical objectives of the project. Model performance is assessed against the predefined success criteria established in the Business Understanding phase. Generalizability is tested by comparing performance across different time periods to determine whether the model performs consistently outside its training window. Error type analysis is conducted to distinguish between false positives and false negatives, which is particularly important in this domain: missing a genuine drought or flood event carries far greater real-world consequences than a false alarm (Relangi, 2024). The phase concludes with a scenario analysis and ethical evaluation, reflecting on potential bias, regional limitations, and the responsible use of the model as a decision-support tool.

## 5.6 Deployment (adapted: proof-of-concept and reporting)

In the standard CRISP-DM model, the final phase concerns the deployment of the developed solution into production (Wirth & Hipp, 2000). Given the scope of this graduation project, full operational deployment is not feasible. Instead, this phase is adapted to the creation of a proof-of-concept including data visualizations and a structured final report. The report is written according to academic reporting guidelines to ensure findings are communicated clearly, reproducibly, and in a format accessible to both technical and non-technical stakeholders (Baarda & Van Vianen, 2021, pp. 279–302). The proof-of-concept will be validated with at least one non-technical stakeholder to assess whether the risk outputs are interpretable and actionable in practice.

# 6. Risk Analysis

Within this project, a machine learning model is developed to predict drought and flood risks in African regions based on ERA5 climate data. The project focuses on the use of large-scale, time-dependent datasets and the necessity to transform complex atmospheric variables into meaningful indicators for climate-related events.

Such data science projects naturally involve various uncertainties, both on a technical, methodological, and organizational level. Limitations in data quality and availability, challenges in defining appropriate target variables, and complexities in model validation can directly affect the reliability and generalizability of the model. In addition, the limited project duration plays an important role in balancing depth, accuracy, and practicality.

Systematically identifying and managing these risks is therefore essential to ensure the quality and usability of the project outcomes and to enable timely adjustments throughout the project. This risk analysis aims to identify the most relevant risks, assess their likelihood and impact, and define appropriate preventive strategies. This allows for proactive management and increases the likelihood of achieving a successful and relevant final result.

| Risk | Likelihood | Impact | Description | Preventive measures |
| --- | --- | --- | --- | --- |
| Insufficient data quality. | Medium | High | Climate data may contain missing values, noise, and inconsistencies, leading to unreliable features and reduced model performance. | Perform exploratory data analysis (EDA), apply data cleaning and imputation, and validate and normalize the data. |
| Complexity of feature engineering. | High | High | Extracting relevant climate indicators (e.g., drought periods or precipitation sums) requires domain knowledge. Poor features result in weak model performance. | Apply iterative feature development and support it with extensive literature research. |
| Unclear target definition. | Medium | High | Droughts and floods are not directly observable, leading to subjective definitions. | Define multiple target combinations based on literature and compare their effectiveness. |
| Insufficient model performance. | Medium | High | Models may not achieve satisfactory and desired performance. | Compare multiple algorithms, optimize hyperparameters, and use appropriate evaluation metrics. |
| Overfitting due to time dependacy. | High | Medium | Time series data can lead to data leakage when using incorrect validation strategies. | Apply time-based splits and cross-validation methods that respect temporal order. |
| Data acces issue (cloud). | Low | Medium | Potential limitations in accessing the Azure environment. | Use local copies or caching mechanisms. |
| Time constraints within project duration. | High | High | The project involves multiple complex components within a limited timeframe, potentially reducing depth, quality or succes of the project. | Work iteratively with clear prioritization. |
| Dependacy on the stakeholders. | Low | Medium | Limited availability of feedback may result in misalignment with expectations. | Schedule regular standup meetings and share intermediate results. |
| Limited model interpretability. | Medium | Medium | Complex models are difficult to interpret, which may reduce stakeholder trust. | Use explanability techniques such as feature importance and SHAP. |
| Limited practical applicability. | Medium | High | Results may not align well with real-world applications of the AI solution. | Focus on understandable outputs (visualizations and risk scores) and relevant use cases. |
| Ethics and bias in data. | Low | Medium | Potential bias in data or model results may lead to incorrect decision-making when using the AI application. | Be transparent about limitations, reflect on bias and explain the tool as a decision-support system. |
| Incorrect or missing references. | Medium | Medium | Insufficient or incorrect referencing of literature and datasets may reduce reliability and violate academic guidelines. | Apply APA guidelines, systematically track sources and verify references |

## 6.1 Analysis of critical risks

The major risks within this project are related to data quality, feature engineering, model validation, and project management.

Firstly, the quality of the climate data represents a major risk. Incomplete or inconsistent data can directly introduce noise into the features, which negatively affects the performance and reliability of the model.

Secondly, feature engineering is a critical step. Transforming raw climate data into relevant features requires both technical expertise and domain knowledge of climate processes. Insufficiently supported features may result in the model failing to capture important patterns.

Model validation in the context of time series data also requires careful attention. Incorrect validation methods can lead to data leakage, causing model performance to appear overly optimistic and resulting in poor real-world performance. Proper handling of the train-test split is therefore essential for a realistic evaluation.

Furthermore, time constraints play a significant role within this project. Given the limited timeframe, the complexity of data processing, modelling, and interpretation may result in reduced depth or quality.

Finally, the practical applicability and interpretability of the model are important considerations. A model may perform well from a technical perspective but still have limited value if the results are not understandable or usable for stakeholders.

## 6.2 Conclusion

The identified risks are largely inherent to machine learning projects involving complex and large-scale datasets. These risks mainly relate to data quality, model development, and the translation of technical results into practical applications.

By applying appropriate methods and techniques, such as iterative development, correct validation strategies, and well-founded feature engineering, these risks can be effectively managed. In addition, attention to interpretability and transparency contributes to the usability and reliability of the model.

Although not all risks can be eliminated, a structured and goal-oriented approach can significantly reduce their impact. This increases the likelihood that the project will result in a successful proof-of-concept for predicting drought and flood risks.

# 7. Final qualifications

| Final qualifications | Activities |
| --- | --- |
| Problem analysis | Conducting literary research on ERA5 climate variables and African agricultural vulnerability to define and sharpen the problem domain. This demonstrates the ability to independently analyze a complex, multi-layered problem and translate it into a concrete and researchable question. |
| Data gathering and -preparation | Apply feature engineering techniques to hourly ERA5 time-series data to construct meaningful drought and flood indicators. This requires professional judgement in selecting and transforming variables, as raw atmospheric parameters do not directly represent climate risk. |
| Modelling | Training, evaluating, and comparing multiple machine learning models using time-based validation strategies and appropriate metrics for imbalanced classification. This demonstrates the ability to make substantiated methodological choices and critically assess model reliability. |
| Reporting and advising | Translating complex model outputs into clear visualizations and actionable risk scores for non-technical stakeholders such as agricultural advisors and policymakers. This demonstrates the ability to communicate findings at the appropriate level for the intended readers. |
| Investigative and reflective attitude and skills | Reflecting on potential bias in ERA5 data, regional limitations of the model and the ethical implications of using AI as a decision-support tool in these vulnerable communities. This demonstrates awareness of the broader societal context and responsibility of data-driven solutions. |

# Reference list

- AbhijeetDataVision. (2025). Data normalization vs standardization: When and why it matters in analysis. Medium. https://medium.com/@AbhijeetDataVision/data-normalization-vs-standardization-when-and-why-it-matters-in-analysis-e8f7702fe0af

- Baarda, B., & Van Vianen, R. (2021). Dit is onderzoek! (4e ed.). Noordhoff.

- Balgah, R. A., Ngwa, K. A., Buchenrieder, G. R., & Kimengsi, J. N. (2023). Impacts of floods on agriculture-dependent livelihoods in Sub-Saharan Africa: An assessment from multiple geo-ecological zones. Land, 12(2), 334. https://doi.org/10.3390/land12020334

- Belcic, I., & Stryker, C. (n.d.). What is feature selection? IBM Think. https://www.ibm.com/think/topics/feature-selection

- Bhuva, L. (2025, March 20). Understanding feature importance in machine learning. Medium. https://medium.com/@lomashbhuva/understanding-feature-importance-in-machine-learning-d86ec50e0055

- Caballar, R. D., & Stryker, C. (n.d.). What is model performance in machine learning? IBM Think. https://www.ibm.com/think/topics/model-performance

- Chalokia, M. (2021, May 2). Time-based splitting and determining if train & test data come from the same distribution. Medium. https://medium.com/@manrajchalokia/time-based-splitting-and-determining-if-train-test-data-come-from-the-same-distribution-e1d2ea881af8

- Chapman, P., Clinton, J., Kerber, R., Khabaza, T., Reinartz, T., Shearer, C., & Wirth, R. (2000). CRISP-DM 1.0: Step-by-step data mining guide. CRISP-DM Consortium.

- Choruma, D. J., Dirwai, T. L., Mutenje, M. J., Mustafa, M., Chimonyo, V. G. P., Jacobs-Mata, I., & Mabhaudhi, T. (2024). Digitalisation in agriculture: A scoping review of technologies in practice, challenges, and opportunities for smallholder farmers in Sub-Saharan Africa. Journal of Agriculture and Food Research, 18, 101286. https://doi.org/10.1016/j.jafr.2024.101286

- Copernicus European Drought Observatory. (2019). Soil moisture anomaly (SMA) factsheet. European Commission, Joint Research Centre. https://drought.emergency.copernicus.eu/data/factsheets/factsheet_soilmoisture.pdf

- CWP. (2025, November 10). Early Warning Systems in Africa - CIMA Research Foundation. CIMA Research Foundation. https://www.cimafoundation.org/en/focus/early-warning-systems/africa/

- Devansh. (2023, April 25). How to properly compare machine learning models. Artificial Intelligence Made Simple. https://www.artificialintelligencemadesimple.com/p/how-to-properly-compare-machine-learning

- ERA5: data documentation - Copernicus Knowledge Base - ECMWF Confluence Wiki. (2026, January 5). https://confluence.ecmwf.int/display/CKB/ERA5%3A+data+documentation

- Fedora, M. A., & Beschta, R. L. (1989). Storm runoff simulation using an antecedent precipitation index (API) model. Journal of Hydrology, 112(1–2), 121–133. https://doi.org/10.1016/0022-1694(89)90184-4

- Ferchichi, A., Ferchichi, A. & Chihaoui, M., (2023). Spatio-temporal modeling of climate change impacts on drought forecast using Generative Adversarial Network: A case study in Africa. Expert Systems With Applications, 238, 122211. https://doi.org/10.1016/j.eswa.2023.122211

- Francis, S. F. (2024, October 5). The importance of feature engineering in data science. Medium. https://medium.com/@silva.f.francis/the-importance-of-feature-engineering-in-data-science-11c45f0f03b0

- Gashure, S. (2024). Adaptation strategies of smallholder farmers to climate variability and change in Konso, Ethiopia. Scientific Reports, 14(1), 19203. https://doi.org/10.1038/s41598-024-70047-9

- Hansen, J. W., Vaughan, C., Kagabo, D. M., Dinku, T., Carr, E. R., Körner, J., & Zougmoré, R. B. (2019). Climate services can support African farmers’ context-specific adaptation needs at scale. Frontiers in Sustainable Food Systems, 3, 21. https://doi.org/10.3389/fsufs.2019.00021

- Horizon Europe. (2026, February 17). Research and Innovation. https://research-and-innovation.ec.europa.eu/funding/funding-opportunities/funding-programmes-and-open-calls/horizon-europe_en

- Jha, G. (2025, September 1). A holistic guide to exploratory data analysis (EDA) for machine learning and deep learning. Medium. https://medium.com/@post.gourang/a-holistic-guide-to-exploratory-data-analysis-eda-for-machine-learning-and-deep-learning-bc4f18f0143b

- Monnik, K. (2000). Role of drought early warning systems in South Africa’s evolving drought policy. In Proceedings of the Expert Group Meeting on Early Warning Systems for Drought Preparedness and Drought Management (pp. 115–123). World Meteorological Organization. https://www.unisdr.org/files/1882_VL102149.pdf

- Motha, R. (2000). Recommendations on drought monitoring by the U.S. National Drought Policy Commission. In Proceedings of the Expert Group Meeting on Early Warning Systems for Drought Preparedness and Drought Management (pp. 106–114). World Meteorological Organization. https://www.unisdr.org/files/1882_VL102149.pdf

- Muzata, S. (n.d.). Africa’s smallholder farmers face collapse if we do not act on climate change. CGIAR System. https://www.cgiar.org/news-events/news/africas-smallholder-farmers-face-collapse-if-we-do-not-act-on-climate-change

- Nandgude, N., Singh, T. P., Nandgude, S., & Tiwari, M. (2023). Drought prediction: A comprehensive review of different drought prediction models and adopted technologies. Sustainability, 15(15), 11684. https://doi.org/10.3390/su151511684

- Nandi, S. (2025, January 13). How to handle class imbalance in machine learning. Medium. https://medium.com/@sushmita2310/how-to-handle-class-imbalance-in-machine-learning-c4eaf8a26026

- Omotoso, A., & Ayodele, M. (2026). Nigerian farmers talk about how climate change is affecting staple food crops – and what can help. The Conversation. https://doi.org/10.64628/aaj.9xg5jra6s

- Prometeia. (2025, February 3). The importance of data quality and validation in machine learning. Prometeia. https://prometeia.com/en/about-us/insights/article/the-importance-of-data-quality-and-validation-in-machine-learning

- Reed, C., Anderson, W., Kruczkiewicz, A., Nakamura, J., Gallo, D., Seager, R., & McDermid, S. S. (2022). The impact of flooding on food security across Africa. Proceedings of the National Academy of Sciences, 119(43), e2119399119. https://doi.org/10.1073/pnas.2119399119

- Relangi, K. S. (2024, June 29). Understanding model evaluation metrics for machine learning. Medium. https://medium.com/@kavyasrirelangi100/understanding-model-evaluation-metrics-for-machine-learning-160d385b72c5

- Singh, A. (2024, December 10). Hyperparameter tuning: Beyond the basics. Medium. https://medium.com/@abhaysingh71711/hyperparameter-tuning-beyond-the-basics-34d36b01448

- Stuart, K. (2025, December 11). The balancing act: Understanding overfitting and underfitting in machine learning. Medium. https://medium.com/@kaylenstuart/the-balancing-act-understanding-overfitting-and-underfitting-in-machine-learning-edae067d12f9

- Teku, D., & Tariku, G. D. (2025). Effectiveness of early-warning systems and disaster risk reduction for rural food security under hydro-meteorological hazards in Sub-Saharan Africa: A systematic review. International Journal of Sustainable Development & World Ecology. https://doi.org/10.1080/13504509.2025.2595056

- Vicente-Serrano, S. M., Beguîría, S., & López-Moreno, J. I. (2010). A multiscalar drought index sensitive to global warming: The Standardized Precipitation Evapotranspiration Index. Journal of Climate, 23(7), 1696–1718. https://doi.org/10.1175/2009JCLI2909.1

- Wirth, R., & Hipp, J. (2000). CRISP-DM: Towards a standard process model for data mining. In Proceedings of the 4th International Conference on the Practical Applications of Knowledge Discovery and Data Mining (pp. 29–39).

- Wilhite, D. A., & Svoboda, M. D. (2000). Drought early warning systems in the context of drought preparedness and mitigation. In Proceedings of the Expert Group Meeting on Early Warning Systems for Drought Preparedness and Drought Management (pp. 1–21). World Meteorological Organization. https://www.unisdr.org/files/1882_VL102149.pdf